## Introduction
Consulting Project Success Tracker |  |  | How to Use this Template
This template helps you manage, and review consulting projects through structured check-ins and clear deliverable tracking. Use the tabs to manage each phase: Dashboard & Scope Define project objectives, success metrics, key deliverables, and ownership from the start. Weekly Progress & Feedback Logs Track weekly updates, risks, decisions, and stakeholder feedback in one place. KPI & Milestone Tracker Monitor project impact and track progress toward defined goals. Use this to assess project health. Risk & Blockers Log and prioritize issues that could delay or derail progress. Use severity to guide action. Each tab is designed to drive clarity, accountability, and speed—ensuring your consultant stays aligned and adds value from day one.
A structured toolkit to align, track, and deliver consulting engagements effectively.
Use this template to define scope, monitor progress, resolve issues, and ensure stakeholder alignment of your project with consultants.
Click to discover more resources

## Dashboard & Scope
Consulting Project Dashboard & Scope
Define project objectives, deliverables, and milestones for full alignment.
Fill in project basics below: key contacts, goals, deliverables, and success metrics. Use the milestone and deliverable tables to define timelines and track weekly status.
Field |  | Description
PROJECT NAME |  | [Insert Project Title]
Consultant Name |  | [Full Name]
Client Company |  | [Company Name]
Internal Sponsor (Main POC) |  | [Name, Role, Email]
Project Start Date |  | [DD/MM/YYYY]
Expected End Date |  | [DD/MM/YYYY]
Business Challenge |  | [“The client is facing high churn among B2B customers..”]
Overall Goal |  | [“Design and implement a customer retention strategy”]
Key Deliverables |  | [Preview of deliverables, overview in the
Success Metrics |  | - [Metric 1: e.g., Increase retention by 10%] - [Metric 2: e.g., Reduce onboarding time by 30%]
Timeline & Milestones |  | Use the subtable below
Achievement Levels
Milestones | 50%
Deliverables | 75%
Milestone | Description | Status | Owner
Kick-off Workshop | Internal alignment session | Done | Consultant
Stakeholder Interviews | Interview 5 internal leaders | In progress | Consultant
Draft Strategy | First version of retention strategy |  | Consultant
Final Presentation | Board-level delivery |  | Consultant
Deliverable | Milestone | Status | Due Date | Format | Description | Deliverables | Feedback Received? | Notes | Overdue?
Competitor Landscape |  | To Do | 2025-01-02 | Excel + PDF Summary | Analysis of top 10 competitors | [Link] | Pending | Draft shared Apr 8 | Overdue
Customer Segmentation |  | Done | [date] | Slide Deck | Personas based on data & interviews | [Link] | In Review
Go-to-Market Plan |  | Done | [date] | 20-slide deck + appendix | Launch options with budget + channels | [Link] | Received
Final Presentation |  | Done | [date] | PPT + Executive Summary | Executive-ready summary of all findings | [Link] | Finalized
|  |  | [date] |  |  | [Link]
|  |  | [date] |  |  | [Link]
|  |  | [date] |  |  | [Link]
|  |  | [date] |  |  | [Link]
Formulas:
Overdue? = IF(AND([Status]<>"Done", TODAY()>[Owner]), "Overdue", "")

## Weekly Progress & Feedback Logs
Weekly Progress & Feedback Logs
Track Check-In Outcomes and Stakeholder Feedback
Note: Use the top log to document weekly updates, blockers, decisions, and next steps. Use the feedback log below to capture stakeholder input on deliverables and track follow-up actions.
Weekly Check-In & Progress Log
Achievement Level
Project Phase | Discovery | 100%
Week # | Project Phase | Due Date | Key Updates / Progress | Blockers / Risks | Decisions Made | Next Steps | % Complete | Owner
1 | Discovery | 2025-03-25 | Kick-off meeting held. Received initial documents (Q4 strategy deck, sales dashboard). Scheduled 5 stakeholder interviews. | No access to CRM yet; Interview with Head of Sales delayed. | Agreed to weekly Monday check-ins. | Chase Sales for CRM access. Reschedule Sales interview. | 100% | Client POC
2 | Discovery | 2025-04-01 | Completed 4/5 stakeholder interviews. Drafted summary of customer pain points. Started mapping retention journey. | Limited visibility on churn reasons due to fragmented data. | Decided to supplement with customer survey. | Draft survey questions; validate with Client. | 100% | Consultant
3 | Analysis | 2025-04-08 | Conducted churn analysis (2022–2024 cohorts). Identified churn spike post-onboarding. | Data gaps in small business segment. | Focus analysis on mid-market customers. | Finalize churn drivers deck. Share with sponsor Apr 10. | 100% | Consultant
4 | Ideation | 2025-04-15 | Outlined 3 intervention ideas. Tested one with Customer Success team. | Resistance from Ops on changing onboarding steps. | Prioritized Option A for pilot design. | Prepare pilot rollout plan for Option A. | 55% | Consultant & Ops Lead
5 | Implementation | 2025-04-22 | Launched pilot with 2 CS teams. Tracking time-to-value KPIs. | Ops SOP updates delayed. Legal review needed. | Approved pilot extension to more teams. | Draft legal-friendly version of email template. | 40% | Consultant & Legal
6 | Implementation | 2025-04-29 | Pilot scaled to 5 teams. Early results: +15% activation rate. | Need better dashboard for KPI tracking. | Build Tableau dashboard for pilot metrics. | Complete dashboard by May 3. | 20% | Data Team
7 | Wrap-Up | 2025-05-06 | Delivered final presentation and Retention Playbook. Client requested roadmap. | None. | Signed off on deliverables. | Handover to PMO. Book feedback session. | 0% | Consultant
Stakeholder Feedback Log
Date | Deliverable / Topic | Stakeholder Name | Role / Department | Feedback Summary | Priority | Action Taken / Planned | Owner | Status | Follow-Up Date
2025-04-08 | Competitor List v1 | Siddarth A. | Head of Strategy | Add 3 French local players. Remove outdated player from 2021. | High | List updated Apr 9 and re-shared. | Consultant | Resolved | 2025-04-10
2025-04-10 | Segmentation Framework | Luca M. | Sales Lead | Looks good—please match segments to existing CRM tags. | Medium | Review CRM structure during next sync. | Consultant | In Progress | 2025-04-16
2025-04-11 | Go-to-Market Options | Maria R. | Marketing | Channel option 2 lacks social media data. | Low | Will add LinkedIn campaign stats in v2. | Consultant | Open | 2025-04-17
2025-04-12 | Draft Report Structure | David K. | CFO | Include financial KPIs in executive summary. | High | Add KPI table and review with Finance. | Consultant | In Progress | 2025-04-15
2025-04-13 | Slide Design Mockup | Sophie L. | Brand & Design | Align slides with internal branding (color & font). | Medium | Request brand guidelines and update deck. | Consultant | Open | 2025-04-18

## KPI & Milestone Tracker
75
KPI & Milestone Tracker
Track the success of your project depending on KPIs, target, and due date
Achievement Levels
| Milestones | 50%
Consulting Project KPI & Milestone Tracker
| Category | KPI / Milestone | Target / Deliverable | Format | Owner | Status | Due Date | Notes
| Stakeholder Engagement | Internal stakeholder interviews completed | 5/5 interviews done | Summary notes | Consultant | Done | Week 2 | One remaining interview scheduled
| Topic Selection | Relevant ESRS topics identified and validated | Min. 90% stakeholder alignment | Preselection list | Consultant | In progress | Week 3 | Based on ESRS 2 + dialogue
| Materiality Analysis | Double materiality matrix developed | Top 10 topics mapped | Slide + matrix | Consultant |  | Week 4 | Will inform strategy priorities
| Strategy Development | Draft strategy submitted | 1st version of full ESRS roadmap | Word / PPT | Consultant |  | Week 5 | Includes topics, KPIs, timeline
| Executive Approval | Strategy approved by steering committee | 100% sign-off | Final PDF deck | Consultant |  | Week 6 | Presentation scheduled
| Reporting Launch Planning | Go-to-market options delivered | 3+ options with budget | Slide deck + Excel | Consultant |  | Week 7 | For internal and external use
| Benchmarking | Competitor ESG landscape completed | 10 profiles summarized | Excel + PDF | Consultant |  | Week 4 | Shared April 8
| Customer Link | ESG-retention risk link identified | 2+ actionable insights | Slide deck | Consultant |  | Week 6 | Supports business case
| Segmentation | ESG-sensitive customer personas | 3+ personas finalized | Slide deck | Consultant |  | Week 5 | Based on interviews & data
Reference Materials Table
| Document Name | Type | Owner / Source | Last Updated | Link / Folder Path | Relevance / Usage | Consultant Access | Notes
| 2024 France Market Entry Report | Past Strategy Project | Strategy Team | 2024-01-01 | [Drive Link] | Context for competitor landscape and GTM structure | Yes | Use to avoid duplication
| CRM Tagging Guidelines | Process Document | Sales Ops | 2023-02-01 | [Drive Link] | Ensure alignment of segmentation output with system tags | Yes | Applies to mid-market personas
| Executive Presentation Template | Slide Template | PMO | 2024-03-01 | [Drive Link] | Format required for final deliverables | Yes | Use only for final deck, not drafts
| Org Chart (Q1 2025) | Internal Resource | HR | 2025-03-01 | [Drive Link] | Identify relevant contacts and team structures | Yes | Check for updated version before Week 4
| Customer Interview Summary – FY23 | Insights Deck | Research & CX | 2023-12-01 | [Drive Link] | Prior pain points to cross-check against current findings | Yes | Add any new patterns to synthesis
| Expense Policy 2025 | Policy Document | Finance | 2025-01-01 | [Drive Link] | Clarifies reimbursable items and thresholds | Yes | Required for all consultant claims
| Strategy OKRs (H1 2025) | Internal Planning Doc | Strategy Team | 2025-04-01 | [Drive Link] | Aligns consultant priorities with strategic goals | Yes | Relevant to all workstreams

## Risk & Blockers
Risk & Blockers Register
Track and Resolve Issues Impacting Project Progress
Log project risks and blockers with impact and probability ratings. Use severity to prioritize. Update resolution plans and status weekly until closed.
Overview
#Total Open Issues |  | 6
% Resolved |  | 0.16667
Count By severity
| Low | 2
| Medium | 1
| High | 3
Count by Type
| #Risks | 4
| #Blockers | 4
ID | Type | Description | Impact | Probability | Severity | Owner | Resolution Plan / Mitigation | Target Resolution Date | Status | Last Updated
R1 | Blocker | CRM access still pending from IT | Medium | High | #NAME? | Client POC | Escalated to IT. Confirm access by Apr 10. | 2025-04-10 | Open | 2025-04-08
R2 | Risk | Sales and Marketing misaligned on GTM approach | High | Medium | #NAME? | Consultant | Run alignment 1:1s ahead of workshop | 2025-04-18 | In Progress | 2025-04-10
R3 | Risk | Final deck may not meet exec formatting standards | Low | Medium | #NAME? | Consultant | Review slide template upfront | 2025-04-22 | Resolved | 2025-04-07
R4 | Blocker | No Finance input for pricing model | High | Medium | #NAME? | Client Sponsor | Request input via email + sync | 2025-04-15 | In Progress | 2025-04-09
R5 | Risk | Low workshop attendance due to team offsite | Medium | Low | #NAME? | Consultant | Send calendar holds, prep async option | 2025-04-23 | Open | 2025-04-10
R6 | Risk | Stakeholder fatigue from overlapping deliverables | Medium | Medium | #NAME? | Consultant + Sponsor | Re-sequence deliverables + use pre-reads | 2025-04-26 | Open | 2025-04-10